## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | SmartSolveAI Unified Chatbot |  | Project Id: |  | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 1
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 3.0.0 |  | Last Updated date: | 30/09/2023 | Project Team Lead: | Eesha patro |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 7 |  |  |  |  | 1
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Language Availability | only 2 language support Hindi and English | Assuming that the target languages have adequate language models and resources available | Project Manager | Moderate |  | Closed | Risk
2 | Risk | Training Data Diversity | Assuming that there is sufficient training data available for each supported language. If the training data is limited, it can affect the chatbot's language understanding and generation capabilities. | Collect a diverse set of training data for each supported language. Seek data sources from various regions and user demographics to capture different language variations. | Project Manager | Low |  | Closed | Assumption
3 | Risk | User Base Expectations | Assuming that users of different languages have similar expectations regarding the chatbot's capabilities and performance | Create language-specific frequently asked questions (FAQs) or help sections to address common user queries and issues in each language. | Project Manager | Low |  | Closed | Issue
4 | Assumption | user should know that answers is generated by bot and not assume it as final answer, technical people should check efficiency of bot before deploy it into production | Enhances user understanding and sets realistic expectations, while also emphasizing the importance of rigorous technical testing before deploying the chatbot into production. | Implement clear and prominent disclaimers that highlight the bot's AI nature and recommend users consult with human experts for critical decisions. | Project Manager | Negligible |  | Open | Dependency
5 | Dependency | NLP Libraries and Models | Relying on third-party NLP libraries and models for language processing means the chatbot's performance and features depend on the availability and quality of these resources. | use language modeules which rasa provides and with only official resources | Project Manager | Negligible |  | Closed
6 | Issue | need to run 2 to 3 servers for different application usecases | makes application hard to maintain and control | by using scripts this issues fixed | Project Manager | Moderate |  | Closed | Open
7 | Issue | may need language experts for NLU data training and data collection and data feeding | requires extra resources | targeting majority language groups first | Project Manager | Negligible |  | Closed | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24